## Summary
Mistri AI | Detailed Project Report — Delhi pilot
First issue, 10 October 2026. Design confirmed with no change. Yellow cells on Inputs and Scope are the inputs.
PROJECT
Name
Place
Kind | IT system for construction workers, contractors, and vendors
Accounts
Length
Channels | Android app, WhatsApp, and a website, in Hindi and English
SCOPE IN FIVE LINES
2. Android app, WhatsApp, and a website, in Hindi and English, on a public cloud in India.
3. A job in text, audio, or a photo becomes a quantity list and a cost estimate, then a vendor match and a booking.
4. Site progress, attendance, and photos are recorded, and an internal invoice is marked unpaid or paid.
5. Sign-in is a phone one-time password. UPI, GST invoicing, and maps are outside this version.
TOTAL COST
Priced subtotal |  | Lines that have a sourced rate.
Contingency |  | Separate from the line rates.
GST |  | Separate from the line rates.
Total |  | Priced subtotal plus contingency plus GST.
Still open |  | Type a rate on Inputs and Scope and the total moves.
TIMELINE
Start
Finish
Duration
KEY RISKS
HOW TO CHANGE A NUMBER
Edit a yellow cell on Inputs and Scope. Rates that are still open are the yellow cells whose value is RATE NEEDED. Replace that word with a number. Do not type over a blue cell. Contingency and GST stay on this cost block and are not inside the unit rates.

## Inputs and Scope
Mistri AI — inputs and scope
Yellow cells with brown type are the only inputs. Change a yellow cell and the sizing, quantities, and totals recalculate. Do not type over a blue figure.
CONFIRMED SCOPE
Project name | Mistri AI | text | Confirmed at intake
Place | Delhi, India | text | Confirmed at intake
Construction workers | 100 | accounts | Pilot cap, confirmed
Contractors | 20 | accounts | Pilot cap, confirmed
Vendors | 20 | accounts | Pilot cap, confirmed
Pilot length | 12 | months | Design, build, and one year of running, confirmed
Languages | 2 | languages | Hindi and English, confirmed
Channels | 3 | channels | Android, WhatsApp, and website, confirmed
VOLUME ASSUMPTIONS
Jobs per contractor per month | 4 | jobs | Assumption 1. A job is counted once.
Description photos per job | 2 | photos | Assumption 2
Audio clips per job | 1 | clips | Assumption 2
Minutes per audio clip | 1 | minutes | Assumption 2. Used only to describe the clip.
Average photo size | 2 | MB | Assumption 9
Average audio size | 1 | MB | Assumption 9
Site updates per job | 12 | updates | Assumption 3
Photos per site update | 1 | photos | Assumption 3
Bookings per job | 2 | bookings | Assumption 4
Catalogue edits per vendor per month | 2 | edits | Assumption 5
Sign-ins per account per month | 8 | sign-ins | Assumption 6. One SMS each.
Share of jobs handled on WhatsApp | 50% | share | Assumption 7
Business WhatsApp messages per WhatsApp job | 16 | messages | Assumption 7. Estimate, match, booking, 12 site replies, invoice.
Share of catalogue edits confirmed on WhatsApp | 50% | share | Assumption 8
Views of each media file during the year | 3 | views | Assumption 11
PLATFORM ASSUMPTIONS
Peak concurrent share of accounts | 20% | share | Assumption 12. Does not reduce the server count.
Database kilobytes per row | 5 | KB | Assumption 13. Metadata only. Photos sit in object storage.
Minimum database volume | 20 | GB | Assumption 13. AWS RDS general-purpose minimum is 20 GiB.
App servers running all month | 2 | servers | Assumption 12. 2 vCPU and 4 GB each, so one can fail.
Hours in a billed month | 730 | hours | Assumption 21. AWS monthly price ÷ hourly price.
Disk per app server | 30 | GB | Assumption 14
Free WhatsApp service messages per month | 1000 | messages | Assumption 15. Set to 0 if messages are billed as utility templates.
Free data transfer out per month | 100 | GB | AWS free allowance, named on the BOM source.
Pilot support days per month | 2 | person-days | Assumption 17
BUILD EFFORT (PLANNING DAYS)
Days — MOD-AUTH phone OTP sign-in | 8 | person-days | Assumption 16
Days — MOD-PROF role and profile | 5 | person-days | Assumption 16
Days — MOD-HOME home and my jobs | 5 | person-days | Assumption 16
Days — MOD-JOB intake of text, audio, and photo | 12 | person-days | Assumption 16
Days — MOD-EST estimate engine | 15 | person-days | Assumption 16
Days — JOB-NEW quantity rules | 6 | person-days | Assumption 16
Days — JOB-EXT quantity rules | 6 | person-days | Assumption 16
Days — JOB-FIT quantity rules | 6 | person-days | Assumption 16
Days — MOD-CAT vendor catalogue | 8 | person-days | Assumption 16
Days — MOD-MATCH locality match | 8 | person-days | Assumption 16
Days — MOD-BOOK find and book | 8 | person-days | Assumption 16
Days — MOD-SITE progress and attendance | 10 | person-days | Assumption 16
Days — MOD-INV internal invoice | 6 | person-days | Assumption 16
Days — CH-AND Android app | 20 | person-days | Assumption 16
Days — CH-WEB website | 15 | person-days | Assumption 16
Days — CH-WA WhatsApp flows | 12 | person-days | Assumption 16
Days — PLT-LANG Hindi and English | 8 | person-days | Assumption 16
Days — PLT-CLOUD environment setup | 6 | person-days | Assumption 16
Days — DAT-ACC schema | 2 | person-days | Assumption 16
Days — DAT-JOB schema | 2 | person-days | Assumption 16
Days — DAT-EST schema | 2 | person-days | Assumption 16
Days — DAT-CAT schema | 2 | person-days | Assumption 16
Days — DAT-BOOK schema | 2 | person-days | Assumption 16
Days — DAT-SITE schema | 2 | person-days | Assumption 16
Days — DAT-INV schema | 2 | person-days | Assumption 16
Days — EXT-OTP integration | 4 | person-days | Assumption 16
Days — EXT-WABA integration | 8 | person-days | Assumption 16
Days — USR-W onboarding | 5 | person-days | Assumption 16
Days — USR-C onboarding | 4 | person-days | Assumption 16
Days — USR-V onboarding | 4 | person-days | Assumption 16
MONEY INPUTS
Build day rate | RATE NEEDED | INR per person-day | No day rate was given and no single published day rate is used. Type a number here to price every build line.
Rupees per US dollar | 96.6149 | INR per USD | FBIL reference rate for 9 October 2026, republished from the RBI website (lawnut.com, retrieved 10 October 2026). The Hindu reported a provisional market close of 96.72 the same day. This cell uses the FBIL reference.
Contingency on priced subtotal | 10% | share | Assumption 18. Planning allowance, not a market rate.
GST on priced subtotal plus contingency | 18% | share | Assumption 19. SMS vendor pages retrieved 10 October 2026 still add GST at 18 percent. A tax adviser confirms which lines are taxable.
PUBLISHED RATES AND OPEN RATES
App server hourly rate | 0.0448 | USD per hour | AWS Price List, EC2 Linux on-demand, t3.medium, Asia Pacific (Mumbai), publication 2026-10-09. 2 vCPU, 4 GiB.
Database hourly rate | 0.053 | USD per hour | AWS Price List, RDS for PostgreSQL, db.t3.small, Single-AZ, Asia Pacific (Mumbai), publication 2026-10-06. 2 vCPU, 2 GiB.
Database disk rate | 0.131 | USD per GB-month | AWS Price List, RDS general-purpose GP3, Single-AZ, Asia Pacific (Mumbai), publication 2026-10-06.
Object storage rate | 0.025 | USD per GB-month | AWS Price List, S3 Standard, first 50 TB, Asia Pacific (Mumbai), publication 2026-09-28.
Object PUT rate | 5e-06 | USD per request | AWS Price List, S3 PUT/COPY/POST/LIST, Asia Pacific (Mumbai), publication 2026-09-28.
Object GET rate | 4e-07 | USD per request | AWS Price List, S3 GET and other requests, Asia Pacific (Mumbai), publication 2026-09-28.
Data transfer out above the free allowance | 0.1093 | USD per GB | National IT Service, AWS S3 India pricing, Mumbai tier after the free 100 GB, retrieved 10 October 2026. The free 100 GB is stated on https://aws.amazon.com/s3/pricing/ retrieved the same day.
Transactional SMS rate | 0.17 | INR per SMS | SMSGatewayCenter published transactional slab, 10,000 units, INR 0.17 per SMS, GST extra, retrieved 10 October 2026.
WhatsApp business message rate | 0.115 | INR per message | Meta WhatsApp Business Platform, India utility and service rate effective 1 October 2026, INR 0.1150, taxes extra. Rate card retrieved 10 October 2026.
Android store registration | 25 | USD once | Google Play Console Help, US$25 one-time registration fee, retrieved 10 October 2026.
TLS certificate | 0 | INR per year | Let's Encrypt, certificates at no charge, https://letsencrypt.org/ retrieved 10 October 2026.
PostgreSQL licence | 0 | INR | PostgreSQL Licence, no fee. https://www.postgresql.org/about/licence/ The hosted instance is charged as the database hourly rate.
Purchased hardware rate | 0 | INR | Confirmed scope: public cloud, and workers use their own phones. Nothing is bought.
Domain name for one year | RATE NEEDED | INR per year | No registrar rate was selected. Type a rupee figure from the registrar invoice.
App-server disk rate | RATE NEEDED | USD per GB-month | Type the current AWS EBS gp3 rate for Asia Pacific (Mumbai). No EBS price file was retrieved for this issue.
Load balancer monthly rate | RATE NEEDED | USD per month | Type the current AWS Application Load Balancer rate for Asia Pacific (Mumbai), or delete the quantity if you will not use one.
Database backup rate above the included allowance | RATE NEEDED | USD per GB-month | Type the current RDS backup rate. AWS includes some backup storage; this line stays open so that allowance is not guessed.
DLT principal-entity registration | RATE NEEDED | INR | Operator fees published in 2026 disagree on whether GST sits inside the figure. Type the operator invoice.
Estimate model fee per job | RATE NEEDED | INR per job | Type a rate only if a separate India-region model is bought. The app servers are already in the cloud lines.
TIMELINE INPUTS
Project start | 2026-10-13 | date | Planning start, the Tuesday after this report. Edit the date.
Build and integrate | 18 | weeks | Assumption 24
Onboarding | 3 | weeks | Assumption 24
Pilot operation | 52 | weeks | Assumption 24. Twelve months counted as 52 weeks.
Close-out | 2 | weeks | Assumption 24
SCOPE STATEMENT CONFIRMED 10 OCTOBER 2026
In scope | Hindi and English tool for a Delhi pilot of up to the worker, contractor, and vendor caps above. Android, WhatsApp, and a website, on a public cloud in India. Phone number and one-time password. One role per account.
In scope | Job types are a new building, an extension or extra floor, and an interior fit-out. The description is text, audio, or a photo. The system returns a cost estimate and a quantity list.
In scope | Vendors type materials, prices, stock, and the Delhi locality they serve. Match uses that locality. Contractors and workers record site progress, attendance, photos, and a saved location, and they raise an internal invoice marked unpaid or paid.
Out of scope | UPI and any money collected in the app. GST invoices and tax filing. Map services and distance. A starting price list or worker list. Aadhaar, bank accounts, and card numbers. A permission system beyond the one-time password, an audit log, and a formal privacy programme.
Out of scope | Users above the pilot caps, work outside Delhi, and construction of the building itself. This report is the software only.

## Assumptions
Mistri AI — assumptions
Each assumption names the input it drives. Change the input, not this text, when you want the numbers to move.
No. | Assumption | Effect on quantity or cost | Input
1 | A job is counted once. Volume is the jobs-per-contractor input. A job a worker creates is inside that count. |  | Jobs per contractor per month
2 | Each job has one text description, the stated number of audio clips, and the stated number of description photos. |  | Photos, audio clips, minutes
3 | Each job has the stated number of site updates, and each update has the stated number of photos plus attendance. |  | Site updates, photos per update
4 | Each job produces one estimate, one material match, the stated number of bookings, and one invoice. |  | Bookings per job
5 | Vendors type every catalogue edit. There is no file to load on day one. |  | Catalogue edits per vendor
6 | Each account signs in at the stated monthly rate. Each sign-in sends one SMS. WhatsApp does not send a second code. |  | Sign-ins per account
7 | The stated share of jobs runs on WhatsApp. Each of those jobs causes the stated number of business messages: estimate, match, booking, one reply per site update, and invoice. | Sets the job part of the WhatsApp message count. | WhatsApp job share and messages per job
8 | The stated share of catalogue edits is confirmed with one WhatsApp message. |  | Vendor WhatsApp share
9 | Photos and audio use the stated average sizes. Text is inside the database row, not in object storage. |  | Photo size, audio size
10 | Media is kept for the whole pilot. Object storage is billed on the growing total, not on the last month alone. |  | Pilot length
11 | Each media file is viewed the stated number of times in the year. Uploads are free of transfer-out charges. |  | Views per file
12 | Peak concurrency is the stated share of accounts. Two app servers still run all month so one can fail. Concurrency does not reduce the hours. |  | Concurrent share, app servers
13 | Each database row is the stated size. The volume billed is the greater of that size and 20 GB, which is the smallest general-purpose RDS volume. |  | Kilobytes per row, minimum volume
14 | Each app server has the stated disk. The GB-months are derived. The rupee rate is open. |  | Disk per app server
15 | WhatsApp messages are treated as service messages, and the published free monthly allowance is subtracted. Set that input to 0 if they are utility templates. |  | Free WhatsApp messages
16 | Build person-days are planning allowances, one per design item. They are not a measured take-off. |  | Days block
17 | After go-live the pilot is supported for the stated days each month. |  | Support days per month
18 | Contingency is the stated percent of the priced subtotal only. Open lines join it automatically once a rate is typed. |  | Contingency
19 | GST is the stated percent of priced subtotal plus contingency, on its own line. A tax adviser confirms which purchases are taxable. |  | GST
20 | US dollar prices convert at the FBIL reference rate on the inputs sheet. |  | Rupees per US dollar
21 | A billed month is 730 hours, which is the divisor AWS uses to show a monthly price from an hourly price. | App-server hours and database hours use this figure. | Hours in a billed month
22 | One load balancer is allowed for the two servers. Its rate is open. |  | Load balancer rate
23 | A separate estimate model, if bought, is one fee per job. It stays open so it is not double-counted with the app servers. |  | Model fee per job
24 | The timeline weeks are planning allowances. They move the dates and do not by themselves move the cost. |  | Week inputs

## Design
Mistri AI — design
Trace key = Yes means a BOQ or BOM line must cite this ID. Screens cite the parent module and are not priced a second time.
COMPONENTS — TRACE KEYS
ID | Kind | Name | Trace key | Role in the pilot
USR-W | User | Construction worker | Yes | Creates jobs, books, views own site updates and invoices
USR-C | User | Contractor | Yes | Worker actions, plus site updates and marking invoices paid
USR-V | User | Vendor | Yes | Catalogue, and invoices that name the vendor
CH-AND | Channel | Android app | Yes | Hindi and English screens
CH-WA | Channel | WhatsApp | Yes | The same tasks as a conversation
CH-WEB | Channel | Website | Yes | The Android screens in a browser
PLT-CLOUD | Platform | Public cloud in India | Yes | Hosts the application and the data for one year
PLT-LANG | Platform | Hindi and English | Yes | Both languages on every channel
EXT-OTP | External | SMS one-time-password gateway | Yes | Sends the code for sign-in
EXT-WABA | External | WhatsApp Business API | Yes | Carries the WhatsApp channel
MOD-AUTH | Module | Phone OTP sign-in | Yes | Phone number and one-time password
MOD-PROF | Module | Role and profile | Yes | One role, trade, and locality
MOD-HOME | Module | Home and my jobs | Yes | Entry point and the account's jobs
MOD-JOB | Module | Job intake | Yes | Text, audio, photo, and job type
MOD-EST | Module | Estimate and quantities | Yes | Cost estimate and quantity list
MOD-CAT | Module | Vendor catalogue | Yes | Materials, price, stock, locality
MOD-MATCH | Module | Material match | Yes | Match by the locality the vendor typed
MOD-BOOK | Module | Find and book | Yes | Find by trade and record the booking
MOD-SITE | Module | Site progress | Yes | Progress, attendance, photos, saved location
MOD-INV | Module | Internal invoice | Yes | Unpaid or paid, no money collected
DAT-ACC | Store | Accounts | Yes | Phone, role, trade, locality, sign-ins
DAT-JOB | Store | Jobs and media | Yes | Text, audio, photos, job type
DAT-EST | Store | Estimates | Yes | Estimate and quantity list
DAT-CAT | Store | Catalogue | Yes | Price, stock, locality
DAT-BOOK | Store | Bookings | Yes | Who was booked, on which job
DAT-SITE | Store | Site records | Yes | Attendance, photos, saved location
DAT-INV | Store | Invoices | Yes | Amount and paid or unpaid
JOB-NEW | Job type | New building | Yes | Quantity rules inside the estimate
JOB-EXT | Job type | Extension or extra floor | Yes | Quantity rules inside the estimate
JOB-FIT | Job type | Interior fit-out | Yes | Quantity rules inside the estimate
SCREENS — EACH CITES ITS PARENT, WHICH IS THE TRACE KEY
ID | Screen | Parent | Channel | Who uses it
SCR-01 | Enter phone number | MOD-AUTH | Android, website | All roles
SCR-02 | Enter one-time password | MOD-AUTH | Android, website | All roles
SCR-03 | Role and profile | MOD-PROF | Android, website | All roles
SCR-04 | Home | MOD-HOME | Android, website | All roles
SCR-05 | My jobs | MOD-HOME | Android, website | Worker, contractor
SCR-06 | New job | MOD-JOB | Android, website | Worker, contractor
SCR-07 | Estimate and quantities | MOD-EST | Android, website | Worker, contractor
SCR-08 | Vendor catalogue | MOD-CAT | Android, website | Vendor
SCR-09 | Material match | MOD-MATCH | Android, website | Worker, contractor
SCR-10 | Find people by trade | MOD-BOOK | Android, website | Worker, contractor
SCR-11 | Booking | MOD-BOOK | Android, website | Worker and contractor named on it
SCR-12 | Site update | MOD-SITE | Android, website | Contractor writes, worker views
SCR-13 | Invoice | MOD-INV | Android, website | Contractor writes, worker and vendor view their own
SCR-W1 | Sign-in conversation | MOD-AUTH | WhatsApp | All roles
SCR-W2 | New job message | MOD-JOB | WhatsApp | Worker, contractor
SCR-W3 | Estimate reply | MOD-EST | WhatsApp | Worker, contractor
SCR-W4 | Catalogue replies | MOD-CAT | WhatsApp | Vendor
SCR-W5 | Match and book replies | MOD-MATCH | WhatsApp | Worker, contractor
SCR-W6 | Site update messages | MOD-SITE | WhatsApp | Contractor writes, worker views
SCR-W7 | Invoice status | MOD-INV | WhatsApp | Each role sees their own
SYSTEM CONTEXT
The diagram uses the same IDs as the table above.

## Sizing
Mistri AI — sizing and quantities
Column D is a formula. Column C is the working in words. Yellow inputs live on Inputs and Scope.
USERS
Key | Measure | Working | Quantity | Unit | Design ID
S-ACC | Registered accounts | Workers + contractors + vendors. |  | accounts | USR-W
S-PEAK | Peak concurrent users | Accounts × the peak share. This records load. Server count stays at the input. |  | users | PLT-CLOUD
JOBS AND RECORDS
S-JOB-M | Jobs per month | Contractors × jobs per contractor. A worker-created job is inside this count so it is not added again. |  | jobs | MOD-JOB
S-JOB-Y | Jobs in the pilot | Jobs per month × months. |  | jobs | MOD-JOB
S-EST | Estimates | One estimate per job. |  | estimates | MOD-EST
S-MATCH | Material matches | One match per job. |  | matches | MOD-MATCH
S-BOOK | Bookings | Jobs × bookings per job. |  | bookings | MOD-BOOK
S-INV | Invoices | One internal invoice per job. |  | invoices | MOD-INV
S-SITE | Site updates | Jobs × site updates per job. |  | updates | MOD-SITE
S-CAT | Catalogue edits | Vendors × edits per month × months. |  | edits | MOD-CAT
S-LOGIN | Sign-ins | Accounts × sign-ins per month × months. |  | sign-ins | MOD-AUTH
S-SMS | OTP text messages | One SMS per sign-in. WhatsApp does not send a second code. |  | SMS | EXT-OTP
STORAGE
S-MB-JOB | Megabytes of media per job | Description photos and site photos at the average photo size, plus audio clips at the average audio size. |  | MB | DAT-JOB
S-MB-DESC | Megabytes of description media per job | Description photos and the audio clip only. |  | MB | DAT-JOB
S-MB-SITE | Megabytes of site media per job | Site photos only. |  | MB | DAT-SITE
S-GB-M | New media per month | Jobs per month × MB per job ÷ 1024. |  | GB | PLT-CLOUD
S-GB-END | Media stored at the end of the pilot | New media each month is kept for the whole pilot, so the last month holds months × the monthly addition. |  | GB | PLT-CLOUD
S-GBMO | Object storage billed | Month 1 stores one month of media, month 2 stores two, and so on. The sum is monthly new × months × (months + 1) / 2. |  | GB-months | PLT-CLOUD
S-GBMO-JOB | Object storage for job descriptions | Total object GB-months × the description share of each job's media. |  | GB-months | DAT-JOB
S-GBMO-SITE | Object storage for site photos | Total object GB-months × the site-photo share. The two shares add back to the total. |  | GB-months | DAT-SITE
DATABASE ROWS AND THE PROVISIONED VOLUME
R-ACC | DAT-ACC rows | One standing account row plus one row per sign-in. |  | rows | DAT-ACC
R-JOB | DAT-JOB rows | One metadata row per job. The file itself is in object storage. |  | rows | DAT-JOB
R-EST | DAT-EST rows | One row per estimate. |  | rows | DAT-EST
R-CAT | DAT-CAT rows | One row per catalogue edit. |  | rows | DAT-CAT
R-BOOK | DAT-BOOK rows | One row per booking. |  | rows | DAT-BOOK
R-SITE | DAT-SITE rows | One row per site update. |  | rows | DAT-SITE
R-INV | DAT-INV rows | One row per invoice. |  | rows | DAT-INV
R-ALL | Database rows | Sum of the seven stores. |  | rows | PLT-CLOUD
S-DB-GB | Calculated database size | Rows × kilobytes per row ÷ 1024 ÷ 1024. |  | GB | PLT-CLOUD
S-DB-PROV | Provisioned database volume | The greater of the calculated size and the 20 GB minimum AWS sells for this volume type. |  | GB | PLT-CLOUD
GB-DAT-ACC | DAT-ACC share of the database bill | This store's share of rows × the provisioned volume × months. The shares add back to the full volume. |  | GB-months | DAT-ACC
GB-DAT-JOB | DAT-JOB share of the database bill | This store's share of rows × the provisioned volume × months. The shares add back to the full volume. |  | GB-months | DAT-JOB
GB-DAT-EST | DAT-EST share of the database bill | This store's share of rows × the provisioned volume × months. The shares add back to the full volume. |  | GB-months | DAT-EST
GB-DAT-CAT | DAT-CAT share of the database bill | This store's share of rows × the provisioned volume × months. The shares add back to the full volume. |  | GB-months | DAT-CAT
GB-DAT-BOOK | DAT-BOOK share of the database bill | This store's share of rows × the provisioned volume × months. The shares add back to the full volume. |  | GB-months | DAT-BOOK
GB-DAT-SITE | DAT-SITE share of the database bill | This store's share of rows × the provisioned volume × months. The shares add back to the full volume. |  | GB-months | DAT-SITE
GB-DAT-INV | DAT-INV share of the database bill | This store's share of rows × the provisioned volume × months. The shares add back to the full volume. |  | GB-months | DAT-INV
BANDWIDTH AND REQUESTS
S-FILES-JOB | Description files | Jobs × (description photos + audio clips). |  | files | DAT-JOB
S-FILES-SITE | Site photo files | Jobs × site updates × photos per update. |  | files | DAT-SITE
S-PUT-JOB | PUT requests for descriptions | One PUT per description file. |  | requests | DAT-JOB
S-PUT-SITE | PUT requests for site photos | One PUT per site photo. |  | requests | DAT-SITE
S-GET-JOB | GET requests for descriptions | Description files × views per file. |  | requests | DAT-JOB
S-GET-SITE | GET requests for site photos | Site files × views per file. |  | requests | DAT-SITE
S-DOWN-Y | Media downloaded in the year | End-state media × views. Uploads are not charged as transfer out. |  | GB | PLT-CLOUD
S-EGRESS-M | Transfer out per month | Annual downloads ÷ months. Views are spread over the year. |  | GB | PLT-CLOUD
S-EGRESS-BILL-M | Billable transfer out per month | Monthly transfer minus the free allowance. The result is zero while the pilot stays inside the allowance. |  | GB | PLT-CLOUD
S-EGRESS-BILL-Y | Billable transfer out in the year | Billable GB per month × months. |  | GB | PLT-CLOUD
LICENCES AND MACHINE HOURS
S-EC2-H | App-server hours | Servers × 730 hours × months. |  | hours | PLT-CLOUD
S-RDS-H | Database hours | One database × 730 hours × months. |  | hours | PLT-CLOUD
S-EBS | App-server disk | Servers × GB per server × months. |  | GB-months | PLT-CLOUD
S-ALB | Load-balancer months | One load balancer for the whole pilot. |  | months | PLT-CLOUD
S-BACKUP | Backup storage allowance | Set equal to the provisioned database, one GB-month per GB per month. The rate stays open. |  | GB-months | PLT-CLOUD
S-WA-M | WhatsApp business messages per month | WhatsApp jobs × messages per job, plus vendor catalogue confirmations. |  | messages | EXT-WABA
S-WA-BILL-M | Billable WhatsApp messages per month | Monthly messages minus the free service allowance. |  | messages | EXT-WABA
S-WA-BILL-Y | Billable WhatsApp messages in the year | Billable messages per month × months. |  | messages | EXT-WABA
S-SUPPORT | Pilot support days | Support days per month × months. |  | person-days | PLT-CLOUD
BUILD DAYS (COPIED FROM INPUTS)
d_MOD-AUTH | Build days MOD-AUTH | Planning allowance. Edit it on Inputs and Scope. |  | person-days | MOD-AUTH
d_MOD-PROF | Build days MOD-PROF | Planning allowance. Edit it on Inputs and Scope. |  | person-days | MOD-PROF
d_MOD-HOME | Build days MOD-HOME | Planning allowance. Edit it on Inputs and Scope. |  | person-days | MOD-HOME
d_MOD-JOB | Build days MOD-JOB | Planning allowance. Edit it on Inputs and Scope. |  | person-days | MOD-JOB
d_MOD-EST | Build days MOD-EST | Planning allowance. Edit it on Inputs and Scope. |  | person-days | MOD-EST
d_JOB-NEW | Build days JOB-NEW | Planning allowance. Edit it on Inputs and Scope. |  | person-days | JOB-NEW
d_JOB-EXT | Build days JOB-EXT | Planning allowance. Edit it on Inputs and Scope. |  | person-days | JOB-EXT
d_JOB-FIT | Build days JOB-FIT | Planning allowance. Edit it on Inputs and Scope. |  | person-days | JOB-FIT
d_MOD-CAT | Build days MOD-CAT | Planning allowance. Edit it on Inputs and Scope. |  | person-days | MOD-CAT
d_MOD-MATCH | Build days MOD-MATCH | Planning allowance. Edit it on Inputs and Scope. |  | person-days | MOD-MATCH
d_MOD-BOOK | Build days MOD-BOOK | Planning allowance. Edit it on Inputs and Scope. |  | person-days | MOD-BOOK
d_MOD-SITE | Build days MOD-SITE | Planning allowance. Edit it on Inputs and Scope. |  | person-days | MOD-SITE
d_MOD-INV | Build days MOD-INV | Planning allowance. Edit it on Inputs and Scope. |  | person-days | MOD-INV
d_CH-AND | Build days CH-AND | Planning allowance. Edit it on Inputs and Scope. |  | person-days | CH-AND
d_CH-WEB | Build days CH-WEB | Planning allowance. Edit it on Inputs and Scope. |  | person-days | CH-WEB
d_CH-WA | Build days CH-WA | Planning allowance. Edit it on Inputs and Scope. |  | person-days | CH-WA
d_PLT-LANG | Build days PLT-LANG | Planning allowance. Edit it on Inputs and Scope. |  | person-days | PLT-LANG
d_PLT-CLOUD | Build days PLT-CLOUD | Planning allowance. Edit it on Inputs and Scope. |  | person-days | PLT-CLOUD
d_DAT-ACC | Build days DAT-ACC | Planning allowance. Edit it on Inputs and Scope. |  | person-days | DAT-ACC
d_DAT-JOB | Build days DAT-JOB | Planning allowance. Edit it on Inputs and Scope. |  | person-days | DAT-JOB
d_DAT-EST | Build days DAT-EST | Planning allowance. Edit it on Inputs and Scope. |  | person-days | DAT-EST
d_DAT-CAT | Build days DAT-CAT | Planning allowance. Edit it on Inputs and Scope. |  | person-days | DAT-CAT
d_DAT-BOOK | Build days DAT-BOOK | Planning allowance. Edit it on Inputs and Scope. |  | person-days | DAT-BOOK
d_DAT-SITE | Build days DAT-SITE | Planning allowance. Edit it on Inputs and Scope. |  | person-days | DAT-SITE
d_DAT-INV | Build days DAT-INV | Planning allowance. Edit it on Inputs and Scope. |  | person-days | DAT-INV
d_EXT-OTP | Build days EXT-OTP | Planning allowance. Edit it on Inputs and Scope. |  | person-days | EXT-OTP
d_EXT-WABA | Build days EXT-WABA | Planning allowance. Edit it on Inputs and Scope. |  | person-days | EXT-WABA
d_USR-W | Build days USR-W | Planning allowance. Edit it on Inputs and Scope. |  | person-days | USR-W
d_USR-C | Build days USR-C | Planning allowance. Edit it on Inputs and Scope. |  | person-days | USR-C
d_USR-V | Build days USR-V | Planning allowance. Edit it on Inputs and Scope. |  | person-days | USR-V
S-DAYS | Build days excluding pilot support | Sum of the planning allowances above. Pilot support is counted on its own line. |  | person-days | PLT-CLOUD
CHECKS
CHK-DB | Database shares minus the full volume (must be 0) | The seven shares must equal provisioned GB × months. |  | GB-months | PLT-CLOUD
CHK-S3 | Object shares minus object total (must be 0) | Description media plus site media must equal all object storage. |  | GB-months | PLT-CLOUD

## BOQ
Mistri AI — bill of quantities
This sheet is the work. The rate of every person-day line reads the single day-rate input. While that input says RATE NEEDED, the amount stays blank.
Line | Phase | Category | Design ID | Description | Quantity | Unit | Rate | Amount (INR) | Source
BQ-01 | Build | Build labour | MOD-AUTH | Build phone OTP sign-in on Android, WhatsApp, and the website |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-02 | Build | Build labour | MOD-PROF | Build role and profile, one role per phone number |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-03 | Build | Build labour | MOD-HOME | Build home and my jobs |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-04 | Build | Build labour | MOD-JOB | Build job intake for text, audio, and photo |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-05 | Build | Build labour | MOD-EST | Build the estimate engine that turns a job into quantities and a cost |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-06 | Build | Build labour | JOB-NEW | Write quantity rules for a new building |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-07 | Build | Build labour | JOB-EXT | Write quantity rules for an extension or extra floor |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-08 | Build | Build labour | JOB-FIT | Write quantity rules for an interior fit-out |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-09 | Build | Build labour | MOD-CAT | Build the vendor catalogue |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-10 | Build | Build labour | MOD-MATCH | Build the locality match |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-11 | Build | Build labour | MOD-BOOK | Build find and book by trade |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-12 | Build | Build labour | MOD-SITE | Build site progress, attendance, photos, and saved location |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-13 | Build | Build labour | MOD-INV | Build the internal invoice and the paid or unpaid mark |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-14 | Build | Build labour | CH-AND | Build the Android app shell |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-15 | Build | Build labour | CH-WEB | Build the website |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-16 | Build | Build labour | CH-WA | Build the WhatsApp conversation |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-17 | Build | Build labour | PLT-LANG | Build Hindi and English across every channel |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-18 | Build | Build labour | PLT-CLOUD | Set up the India-region cloud environment |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-19 | Build | Build labour | DAT-ACC | Create the account store |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-20 | Build | Build labour | DAT-JOB | Create the job store |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-21 | Build | Build labour | DAT-EST | Create the estimate store |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-22 | Build | Build labour | DAT-CAT | Create the catalogue store |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-23 | Build | Build labour | DAT-BOOK | Create the booking store |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-24 | Build | Build labour | DAT-SITE | Create the site store |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-25 | Build | Build labour | DAT-INV | Create the invoice store |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-26 | Build | Build labour | EXT-OTP | Connect the SMS one-time-password gateway |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-27 | Build | Build labour | EXT-WABA | Connect the WhatsApp Business API |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-28 | Build | Build labour | USR-W | Prepare worker onboarding for the pilot |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-29 | Build | Build labour | USR-C | Prepare contractor onboarding for the pilot |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-30 | Build | Build labour | USR-V | Prepare vendor onboarding for the pilot |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BQ-31 | Run | Build labour | PLT-CLOUD | Support the pilot after go-live |  | person-days |  |  | Day rate is the yellow input on Inputs and Scope. No day rate was supplied and no published day rate is used, so the cell stays RATE NEEDED until you type a number.
BOQ total (blank amounts are ignored)

## BOM
Mistri AI — bill of materials
Hardware, software, and services to buy or license. Quantity comes from Sizing. Rate comes from Inputs and Scope. Amount converts USD at the FBIL rate and stays blank when the rate is RATE NEEDED.
Line | Phase | Section | Category | Design ID | Item | Specification | Make or equivalent | Quantity | Unit | Rate | Currency | Amount (INR) | Source
BM-01 | Build | Hardware | Hardware | PLT-CLOUD | Servers and phones | No device is purchased. The pilot runs on the public cloud and on the users' own Android phones. | None |  | number |  | INR |  | Confirmed scope, 10 October 2026.
BM-02 | Build | Software | Certificates and accounts | CH-AND | Android store account | One Play Console developer account, once. | Google Play or equivalent store |  | account |  | USD |  | Google Play Console Help, US$25 one-time fee, retrieved 10 October 2026. https://support.google.com/googleplay/android-developer/answer/6112435
BM-03 | Build | Software | Certificates and accounts | CH-WEB | Domain name | One name for one year, .in or .com. | Any ICANN registrar |  | year |  | INR |  | RATE NEEDED. No registrar was chosen.
BM-04 | Build | Software | Certificates and accounts | PLT-CLOUD | TLS certificate | One certificate for the website, renewed through the pilot. | Let's Encrypt or equivalent |  | year |  | INR |  | Let's Encrypt, no charge, retrieved 10 October 2026. https://letsencrypt.org/
BM-05 | Build | Software | Certificates and accounts | PLT-CLOUD | Database software licence | PostgreSQL for all seven stores. The machine is priced on the database hourly line. | PostgreSQL |  | licence |  | INR |  | PostgreSQL Licence, no fee. https://www.postgresql.org/about/licence/
BM-06 | Run | Services | Cloud | PLT-CLOUD | App servers | Two machines, 2 vCPU and 4 GB memory, Linux, running all month in India, for the pilot length. | Amazon EC2 t3.medium or equivalent |  | hours |  | USD |  | AWS Price List, EC2 Linux on-demand t3.medium, Asia Pacific (Mumbai), USD 0.0448 per hour, publication 2026-10-09.
BM-07 | Run | Services | Cloud | PLT-CLOUD | Database server | One PostgreSQL instance, 2 vCPU and 2 GB memory, Single-AZ, India region. | Amazon RDS db.t3.small or equivalent |  | hours |  | USD |  | AWS Price List, RDS PostgreSQL db.t3.small Single-AZ, Asia Pacific (Mumbai), USD 0.053 per hour, publication 2026-10-06.
BM-08 | Run | Services | Cloud | PLT-CLOUD | App-server disk | 30 GB general-purpose disk on each app server, for the pilot length. | Amazon EBS gp3 or equivalent |  | GB-months |  | USD |  | RATE NEEDED. Enter the current Mumbai gp3 USD rate in the yellow input.
BM-09 | Run | Services | Cloud | PLT-CLOUD | Load balancer | One load balancer in front of the two app servers. | Amazon ALB or equivalent |  | months |  | USD |  | RATE NEEDED. Enter the current Mumbai monthly USD rate, or set the sizing quantity aside if you will not use one.
BM-10 | Run | Services | Cloud | PLT-CLOUD | Database backup | Backup held equal to the provisioned database for each month. | Amazon RDS backup or equivalent |  | GB-months |  | USD |  | RATE NEEDED. AWS includes some backup storage. The rate stays open so that allowance is not guessed.
BM-11 | Run | Services | Cloud | PLT-CLOUD | Data transfer out | Downloads of media above the free monthly allowance. Uploads are not charged. | AWS data transfer or equivalent |  | GB |  | USD |  | Free 100 GB per month stated on https://aws.amazon.com/s3/pricing/ retrieved 10 October 2026. Paid tier USD 0.1093 per GB from National IT Service, AWS S3 India pricing, retrieved the same day.
BM-12 | Run | Services | Cloud | DAT-ACC | Account-store share of database disk | This store's share of the one provisioned database volume. | Amazon RDS gp3 or equivalent |  | GB-months |  | USD |  | AWS Price List, RDS GP3 Single-AZ, Mumbai, USD 0.131 per GB-month, publication 2026-10-06. Share is a formula so the seven stores add up to the volume.
BM-13 | Run | Services | Cloud | DAT-JOB | Job-store share of database disk | Metadata only. The audio and photos are on the object-storage line. | Amazon RDS gp3 or equivalent |  | GB-months |  | USD |  | Same RDS GP3 rate, publication 2026-10-06.
BM-14 | Run | Services | Cloud | DAT-EST | Estimate-store share of database disk | This store's share of the one volume. | Amazon RDS gp3 or equivalent |  | GB-months |  | USD |  | Same RDS GP3 rate, publication 2026-10-06.
BM-15 | Run | Services | Cloud | DAT-CAT | Catalogue-store share of database disk | This store's share of the one volume. | Amazon RDS gp3 or equivalent |  | GB-months |  | USD |  | Same RDS GP3 rate, publication 2026-10-06.
BM-16 | Run | Services | Cloud | DAT-BOOK | Booking-store share of database disk | This store's share of the one volume. | Amazon RDS gp3 or equivalent |  | GB-months |  | USD |  | Same RDS GP3 rate, publication 2026-10-06.
BM-17 | Run | Services | Cloud | DAT-SITE | Site-store share of database disk | Metadata for attendance and location. Photos are on the object-storage line. | Amazon RDS gp3 or equivalent |  | GB-months |  | USD |  | Same RDS GP3 rate, publication 2026-10-06.
BM-18 | Run | Services | Cloud | DAT-INV | Invoice-store share of database disk | This store's share of the one volume. | Amazon RDS gp3 or equivalent |  | GB-months |  | USD |  | Same RDS GP3 rate, publication 2026-10-06.
BM-19 | Run | Services | Cloud | DAT-JOB | Description media storage | Text stays in the database. Audio and description photos sit here, kept for the whole pilot. | Amazon S3 Standard or equivalent |  | GB-months |  | USD |  | AWS Price List, S3 Standard first 50 TB, Mumbai, USD 0.025 per GB-month, publication 2026-09-28.
BM-20 | Run | Services | Cloud | DAT-SITE | Site-photo storage | Site photos, kept for the whole pilot. | Amazon S3 Standard or equivalent |  | GB-months |  | USD |  | Same S3 Standard rate, publication 2026-09-28.
BM-21 | Run | Services | Cloud | DAT-JOB | Description upload requests | One PUT per description file. | Amazon S3 or equivalent |  | requests |  | USD |  | AWS Price List, S3 PUT, Mumbai, USD 0.000005 per request, publication 2026-09-28.
BM-22 | Run | Services | Cloud | DAT-SITE | Site-photo upload requests | One PUT per site photo. | Amazon S3 or equivalent |  | requests |  | USD |  | Same S3 PUT rate, publication 2026-09-28.
BM-23 | Run | Services | Cloud | DAT-JOB | Description download requests | One GET per view of a description file. | Amazon S3 or equivalent |  | requests |  | USD |  | AWS Price List, S3 GET, Mumbai, USD 0.0000004 per request, publication 2026-09-28.
BM-24 | Run | Services | Cloud | DAT-SITE | Site-photo download requests | One GET per view of a site photo. | Amazon S3 or equivalent |  | requests |  | USD |  | Same S3 GET rate, publication 2026-09-28.
BM-25 | Run | Services | Messaging | EXT-OTP | One-time-password SMS | One transactional SMS per sign-in, India DLT route. | SMSGatewayCenter or equivalent |  | SMS |  | INR |  | SMSGatewayCenter published transactional slab, 10,000 units, INR 0.17 per SMS, GST extra, retrieved 10 October 2026.
BM-26 | Build | Services | Messaging | EXT-OTP | DLT registration | Principal entity and one sender header, required before OTP SMS will be delivered. | Jio, Airtel, or Vi DLT |  | registration |  | INR |  | RATE NEEDED. Published 2026 operator fees disagree on whether GST is inside the figure.
BM-27 | Run | Services | Messaging | EXT-WABA | WhatsApp business messages | Billable service messages after the free monthly allowance. Taxes extra. | Meta WhatsApp Business Platform |  | messages |  | INR |  | Meta India utility and service rate INR 0.1150 effective 1 October 2026, taxes extra. Free allowance 1,000 service messages per phone number per month. Retrieved 10 October 2026.
BM-28 | Run | Services | Model | MOD-EST | Estimate model | One generation per job from text, audio, or a photo, processed in India. Leave RATE NEEDED if this stays on the app servers. | Any India-region model |  | jobs |  | INR |  | RATE NEEDED. No India-region model price was selected.
BOM total (blank amounts are ignored)

## Timeline
Mistri AI — timeline
Durations are the yellow week inputs. Dates are formulas from the start date. They are a plan, not a promise.
Phase | Milestone | Depends on | Duration (weeks) | Start | Finish | Design IDs
Design | Design confirmed. Confirmed scope and this design | None |  |  |  | All trace keys
Build | Build and integrate. Android, WhatsApp, website, and cloud environment ready | Design |  |  |  | Modules, channels, stores, EXT-OTP, EXT-WABA
Onboarding | Pilot onboarding. Workers, contractors, and vendors can sign in | Build |  |  |  | USR-W, USR-C, USR-V
Run | Pilot operation. One year of use inside the pilot caps | Onboarding |  |  |  | PLT-CLOUD
Close-out | Pilot review. Quantities and open rates reviewed against actual use | Run |  |  |  | PLT-CLOUD
Pilot finish |  | Weeks from start

## Cost Summary
Mistri AI — cost summary
Contingency and GST are separate from the line rates. Lines marked RATE NEEDED are counted and are not in the rupee total.
Category | Build (INR) | Run (INR) | Total (INR) | What is included
Build labour |  |  |  | Person-days. Blank until the day rate is typed.
Cloud |  |  |  | From the BOM. A blank category still has lines marked RATE NEEDED.
Messaging |  |  |  | From the BOM. A blank category still has lines marked RATE NEEDED.
Certificates and accounts |  |  |  | From the BOM. A blank category still has lines marked RATE NEEDED.
Hardware |  |  |  | From the BOM. A blank category still has lines marked RATE NEEDED.
Model |  |  |  | From the BOM. A blank category still has lines marked RATE NEEDED.
Priced subtotal |  |  |  | Sum of amounts that have a numeric rate.
Contingency |  |  |  | Percent of the priced subtotal. It is not hidden inside the line rates.
GST |  |  |  | Percent of priced subtotal plus contingency. Confirm taxable lines with a tax adviser.
Total with contingency and GST |  |  |  | Excludes every line still marked RATE NEEDED.
BOQ lines still RATE NEEDED
BOM lines still RATE NEEDED
RECONCILIATION
BOQ total
BOM total
BOQ plus BOM
Matches priced subtotal
BY CHANNEL OF BUY
Hardware
Software
Services

## Risks and Compliance
Mistri AI — risks and compliance
Effects that can be calculated point at the workbook. The rest are conditions to watch.
ID | Risk | What it does to the pilot | Effect on this report | Level | Design IDs | Response
R1 | Build day rate is open | The person-day quantities are in the BOQ. They have no rupee amount until the day-rate input is filled. That labour is likely to be larger than the cloud bill. |  | High | All build IDs | Type a day rate on Inputs and Scope. Every labour line then prices itself.
R2 | WhatsApp messages may all be billable | The quantity subtracts 1,000 free service messages a month. If Meta treats these messages as utility templates, that allowance does not apply. |  | Medium | EXT-WABA, CH-WA | Set the free-allowance input to 0 and the BOM recalculates. Keep marketing messages out of the pilot.
R3 | Worker data with OTP only | The pilot stores name, phone, trade, photos, audio, and a saved location. The confirmed security bar is a one-time password, with no audit log and no formal privacy programme. | A complaint or a DPDP notice can stop the pilot. It does not change a quantity until the scope changes. | High | DAT-ACC, DAT-JOB, DAT-SITE, MOD-AUTH | Before go-live, add a short privacy notice and a way to delete an account, as a scope change.
R4 | SMS will not arrive without DLT | India requires a registered principal entity and a template before transactional SMS is delivered. Sign-in depends on that SMS. | The registration line is RATE NEEDED. Login quantity is already counted. | High | EXT-OTP, MOD-AUTH | Start DLT registration during the build phase, not on the week of go-live.
R5 | Estimates use typed vendor prices | There is no starting price list and no map. A match can only use what the vendor typed, including a wrong locality or a stale price. | No cost line changes. Estimate quality is the product risk. | Medium | MOD-CAT, MOD-MATCH, MOD-EST | Show the vendor's typed date on the match screen so the contractor sees how old the price is.
R6 | Single database zone | The database price is a Single-AZ instance. A zone failure takes the pilot offline. | A second zone is a different AWS rate. It is not in this issue. | Medium | PLT-CLOUD, DAT-ACC | Accept the downtime for the pilot, or price a Multi-AZ instance as a change.
R7 | Dollar prices move | Cloud lines are USD rates converted at the FBIL rate of 9 October 2026. | Edit the rupees-per-dollar input. Every USD line recalculates. | Low | PLT-CLOUD | Replace the FX input with the FBIL rate on the day you place the order.
R8 | Model fee is open | Hindi speech and photo estimates may need a paid model. The app servers are already priced. A separate model must not be added twice. | The model line is one per job and stays RATE NEEDED. | Medium | MOD-EST, MOD-JOB | If the model runs on the two app servers, leave the rate as RATE NEEDED.
COMPLIANCE
ID | Rule | How it touches this pilot | Where it sits in the report
C1 | DPDP Act 2023 | Phone numbers, names, photos, audio, and location are personal data. The confirmed pilot does not include a privacy programme. | Treat the risk R3 response as a gate before real workers are invited.
C2 | TRAI commercial-communication rules | OTP SMS needs DLT registration, a header, and a template. | Priced as a RATE NEEDED registration plus the SMS rate.
C3 | Meta WhatsApp Business policy | Business-initiated messages follow Meta's categories and the rate card of 1 October 2026. | The BOM uses the India service and utility rate and the published free allowance.
C4 | GST on this project | The product does not raise GST invoices. The project's own purchases can still attract GST. | GST is a separate line at the input rate, not inside the unit rates.
C5 | Payments | The pilot does not collect money, so it does not need a payment-aggregator licence. | UPI stays out of scope. The invoice is a record of paid or unpaid.
C6 | Maps and location | A location saved with a site update is a record. It is not sent to a map service. | No map licence is in the BOM.

## Change Log
Mistri AI — change log
Corrections after your feedback are added here and applied everywhere they apply.
No. | Date | Where | What changed | Carried into
CL-01 | 2026-10-10 | Scope | Scope confirmed with no change. | Inputs and Scope
CL-02 | 2026-10-10 | Design | Design confirmed with no change to IDs, screens, or roles. | Design, BOQ, BOM
CL-03 | 2026-10-10 | Trace rule | Screen IDs stay under the parent module and are not priced a second time. This was the rule in the confirmed design. | BOQ, BOM
CL-04 | 2026-10-10 | Rates | No rate was invented. Published rates are named with their date. Every other rate is the input RATE NEEDED and its amount is blank. | BOQ, BOM, Cost Summary
CL-05 | 2026-10-10 | Self-check | Checked before issue: every trace ID has a line, every line cites a trace ID, quantities are formulas from Sizing, totals reconcile, and every numeric rate has a source. | Cost Summary reconciliation
CL-06 | 2026-10-10 | Cost Summary | A category with no numeric rate is left blank. It is not shown as zero, so the open day rate and the open model fee are not read as a free item. | Summary total